{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":24,"n_cols":8,"rows_kept":24,"cut":false,"hidden":false,"merged":[[0,0,2,7]]}
["Sample Plan and Schedule"]
[]
[]
[null,"Activity Name","Description","Source(s) Addressed","Outcome(s) Expected","Resource(s) Needed","Target Start Date","Target End Date"]
["Activity 1","Septic Education","Develop and mail out education materials for septic systems.","wastewater","education and engagement from homeowners on proper septic maintenance","Staff time, Funds to print","2026-04-01","2027-02-01"]
["Activity 1A","Develop materials","Develop educational materials for nitrogen pollution linked to septic systems for residential and business/commercial properties.","wastewater","materials to distribute to engage homeowners","Staff time, Funds to print","2026-04-01","2027-12-31"]
["Activity 1B","Mail materials","Send out septic materials in school tax bill.","wastewater","engagement of homeowners","Staff time","2027-01-01","2028-02-01"]
["Activity 2","Municipality's Fertilizer Use - Stop","No fertilizer use on municipal properties. Draft memo and send out to DPW and facilities.","fertilizer","reduction of 2.0 lbs/day of nitrogen (additional cost savings)","Memo to staff","2027-04-01","2028-05-01"]
["Activity 3","Residential Fertilizer Use","Develop and mail out education materials for fertilizer use on residential properties.","fertilizer","education and engagement from homeowners on proper fertilizer use","Staff time, Funds to print","2027-04-01","2028-07-31"]
["Activity 3A","Develop materials","Develop education materials for fertilizer use on residential properties to limit nitrogen leaching and runoff.","fertilizer","materials to distribute to engage homeowners","Staff time, Funds to print","2027-04-01","2028-05-31"]
["Activity 3B","Mail materials","Mail educational materials with property tax bill.","fertilizer","engagement of homeowners","Staff time","2027-06-01","2028-07-31"]
["Activity 4","Municipal Fertilizer Regulation","Enact fertilizer reduction legislation based on research into LINAP Recommendations, other local fertilizer laws, and town board input.","fertilizer","reduction of nitrogen fertilizer load","Staff time, legal time, enforcement discussions","2027-01-01","2027-12-31"]
["Activity 5","Nitrogen Removal Upgrade WWTP #4","Upgrade WWTP#4 with nitrogen removal.","wastewater","removal of 2.0 lbs/day of nitrogen from effluent into the receiving waterbody","Staff time, Funds for contractors, Grant applications, Funds for grant match","2026-10-01","2027-12-31"]
["Activity 5A","Apply for grant funds for feasibility study at WWTP #4.","Apply to grant program for funds.","wastewater","grant application","Staff time","2026-10-01","2027-12-31"]
["Activity 5B","Feasibility Study for Nitrogen Reduction at WWTP #4","Conduct a feasibility study to determine what type of nutrient removal can occur at WWTP #4. ","wastewater","determination on type of technology that can be constructed at WWTP #4 to remove at least an additional 2.0 lbs/day of nitrogen.","Staff time, $$ for contractors","2027-01-01","2028-12-31"]
["Activity 5C","Develop a design/plan to implement the results of WWTP #4 feasibility study.","Issue an RFP for the design of the nutrient removal practice determined in Action 5B.","wastewater","design/plan for nutrient removal construction at WWTP #4","Staff time, $$ for contractors","2027-01-01","2028-12-31"]
["Activity 5D","Apply for grant funds to construct upgrade to WWTP #4","Apply to NYS WQIP grant program for funds to construct nutrient removal at WWTP #4.","wastewater","grant application","Staff time","2027-04-01","2027-06-30"]
["Activity 5E","RFP to construct upgrade to WWTP #4.","Issue RFP for construction of nutrient removal upgrade to WWTP #4 ","wastewater","RFP for construction","Staff time","2026-07-01","2027-12-31"]
["Activity 5F","Construct upgrade to WWTP #4.","Construct nutrient removal upgrade to WWTP #4 ","wastewater","construct nutrient removal at WWTP #4 to remove 2.0 lbs/day of nitrogen.","Staff time, grant match $$","2027-01-01","2028-12-31"]
["Activity 6","Review Stormwater Guidance.","Review municipal stormwater guidance to ensure it is up to date and being followed.","stormwater","potential updates to guidance","Staff time","2027-04-01","2027-06-30"]
["Activity 7"]
["Activity 8"]
["Activity 9"]
["Activity 10"]